## Slide 1: Aims
Specific Aim 1: Assess experiences and needs
  We will enhance our current mutual aid to include COVID supplies (e.g. masks, hand sanitizer) and referrals, and will systematically assess community needs by gathering data and firsthand narratives.
Specific Aim 2: Develop and implement locally-appropriate interventions.
  The in-depth knowledge gathered in Specific Aim 1 will be archived, analyzed, and shared with a coalition of local organizations and community members. By participating in and convening meetings and by providing micro-grants, we will develop and implement locally-appropriate community-based interventions.

## Slide 2: Phase 1 Progress
Training
  Study team participated in training for: Human Subjects Research, Research Ethics, Data Management Practices, De-escalation, Mutual Aid Work, CPR, First Aid, and Narcan Delivery
Coalition Development
  Streetvibes: participated in training, micro-grant decision, and modification of qualitative data collection
  Food Not Bombs: participated in mutual aid efforts
  PIs working on getting connected with potential community stakeholders and partners

## Slide 3: Phase 1 Progress (cont.)
Mutual Aid
  Distributed approximately 600 disposable masks and 252 ounces of hand sanitizer (in various sizes)
  Supplied food, drinks, clothing, hygiene items, and basic first aid materials to community members
  Challenges: Unable to order more supplies; Determining best and just way to distribute micro-grant money
  Response: Have received budget string and working to restock supplies; Determined that $10 bus passes and $5-10 Kroger gift cards will be purchased with micro-grant money

## Slide 4: Phase 1 Progress (cont.)
Recruitment
  15 participants enrolled in the study (screened 17)
    Majority were recently released from HCJC (8; 53% of sample)
  Challenges: staff availability (i.e., some quarantined due to COVID concerns), variable work hours (due to missing peak release times, weather conditions, and removal by HCJC staff), unintended emphasis those being released from HCJC, and community members’ not approaching the Jail Support tent
  Response: Incorporating trained volunteers into mutual aid/data collection, modifying work hours to match release patterns, retrieval of County permit to conduct work, assigning staff to recruitment of one targeted population during shift, and tracking the number of individual that are released from HCJC but do not approach the Jail Support tent

## Slide 5: Phase 1 Progress (cont.)
Data Collection
  8 participants (53%) had reported some COVID symptoms or recent exposure
    2 participants attributed symptoms to treatment while in HCJC
  Qualitative data collected on community needs & resources
    Many participants reported general and COVID-specific needs around job, housing, and financial support
  Challenges: Unable to collect temperature; Lack standardized list of testing sites; Data saturation reached
  Responses: Ordered thermometers; Have a testing site list ready for distribution; Modifying qualitative data instrument to focus on COVID response within congregate care settings (e.g., HCJC and local shelters)

## Slide 6: Phase 2 & 3 Plans
In addition to outlined responses:
  Trainings: Setting up interview training for P2 and investigating vicarious trauma training for P2/3
  Coalition Building: Continue making relevant connections and seeing how we can folds their needs/desire for data into our work
  Website Development: working with an archivist to organize and present data
  Data Analysis: Ongoing and will carry out qualitative data analysis in P3
  Sharing Findings
    Preparing data to share with community partners and those active in COVID response
    Determining what academic routes we can take with data (e.g., poster presentation, academic journals)
  Looking for grants/funding to continue work long-term